## Sheet1
Task | Owner | Status | Priority | Start Date | Due Date | Dependency | Remarks
Requirement Finalization | Business Analyst / PM | Completed | High | 2026-10-01 | 2026-10-03 | None | Requirements finalized
UI/UX Design | UI/UX Designer | Completed | High | 2026-10-04 | 2026-10-08 | Requirement Finalization | Design completed
Frontend Development | Frontend Developer | In Progress | High | 2026-10-09 | 2026-10-20 | UI/UX Design | Development in progress
Backend Development | Backend Developer | In Progress | Critical | 2026-10-09 | 2026-10-21 | Requirement Finalization | Development in progress
API Development | API Developer | In Progress | Critical | 2026-10-12 | 2026-10-22 | Backend Development | APIs under development
QA Testing | QA Team | Not Started | Critical | 2026-10-23 | 2026-10-27 | Frontend, Backend & API | To start after stable build
Bug Fixing | Development Team | Not Started | Critical | 2026-10-28 | 2026-10-30 | QA Testing | Fix defects identified by QA
Regression Testing | QA Team | Not Started | High | 2026-10-31 | 2026-11-02 | Bug Fixing | Verify fixes
UAT | Business / User Team | Not Started | High | 2026-11-03 | 2026-11-05 | Regression Testing | User acceptance testing
Production Release | DevOps / PM | Not Started | Critical | 2026-11-06 | 2026-11-06 | UAT | Release after UAT approval
Assumptions
Dates are assumed for assignment purposes because actual project dates were not provided.
Frontend and backend development can proceed in parallel after requirements are finalized
QA starts after a stable build is available
UAT starts after successful regression testing
Production release is planned after UAT approval.